## 易书馆用户故事
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h）
1 | 1 | 1 | user story | 预约座位 | 作为一个爱忘事的用户，我希望已预约座位快过期前能够给与一个友好的提示，以便我及时打卡避免记过 | Initial Feature | Not Done | 2 | 98 |  |  | 2
1 | 1 | 1 | user story | 预约座位 | 作为一个喜欢仪式感的用户，我希望系统能够记住我常预约的座位，以便下次能够快捷选座 | Initial Feature | Not Done | 2 | 98 |  |  | 2
1 | 1 | 1 | user story | 续借图书 | 作为一个爱忘事的用户，我希望在图书快到期之前能够给与友好的提示，以免错过续借期 | Initial Feature | Not Done | 2 | 98 |  |  | 2
1 | 1 | 1 | user story | 新书速递 | 作为一个书虫，我希望有一个能够查看新进图书的界面，这样我就能及时获取最新图书的信息 | Initial Feature | Not Done | 2 | 98 |  |  | 2
1 | 1 | 1 | user story | 需求反馈 | 作为图书管理员，我想要一个了解同学们需求的平台，以便及时采购同学们想要阅读的图书 | Initial Feature | Not Done | 2 | 98 |  |  | 2
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker